## Schedule&Milestone
Delivery | Sprints | Activities | Months
|  |  | 1 | 2 | 3 |  |  | 4 | 5 | 6 | 6.5
0 | Project Statup
Environment Setup
LLD Template Finalisation
Test Lab Setup At TCS
Delivery 1 | Sprint 0 | Engine
| Sprint 1 | Specification Driven configuration/ Safety Limits
| Sprint 2 | Generic Dash-board based configuration
| Sprint 3 | Element Node Manager Application
| Sprint 4 | LMC GUI screens Partial
| Sprint 5 | Servo Control
| Sprint 6 | OFS
| Sprint 7 | Sentinel
Interim Review- Get Early feedback on the Software
| Sprint 8 | FPS
| Sprint 9 | FE
| Sprint 10 | LMC Master Control GUI Suite
Share with NCRA for early feedback
Delivery 2 | Completion of Delivery 1- Feedback Release Backlog
| Sprint 11 | Rollover of Subsystems at 2 Antenna System
| Sprint 12 | GAB (LMC & CMC)
| Sprint 13 | Central Node (Package)
| Sprint 14 | Master Control GUI Suit
| Sprint 15 | Fault Management & Basic Diagnostic Application
| Sprint 16 | Element Node System Start-up/ Shutdown
| Sprint 17 | False Alarms
Share with NCRA for early feedback
Delivery 3 | Completion of Delivery 2- Feedback Release Backlog
| Sprint 18 | Aggregation Node Manager Application
| Sprint 20 | Longevity Unit & Resource Manager
| Sprint 21 | Array Manager GUI Suite
| Sprint 22 | Electrical Power ON at Subsystems & LMC & CMC
UAT Testing for Phase 1
Feedback Release Backlog
Phase I Acceptance/ Project Closure
NOTES | [5 empty] | LEGENDS
1. Setting safety limits, testing, alarm configuration and false alarm is inherent part of individual sprints 2. Feedback on previous delivery will be incorporated in the next delivery. | [6 empty] | Payment Milestone |  |  | Time Lines
[7 empty] | Parallel Activity At NCRA |  |  | UAT/NCRA Early Feedback
Feedback Release Backlog
M
M
M
M
M
M

## Important Dates
Sr. No. | 0.26 Ver of Schedule |  | Proposal Schedule
| Milestone | Week Since Project Started | Milestone | Week Since Project Started
1 | Project Startup | Month 1: Week 1 | Project Startup | Month 1: Week 1
3 | Interim Review | Month 4: Week 2 | Interim Review | Month 4: Week 1
4 | Delivery 1 | Month 5: Week 1 | Delivery 1 | Month 4: Week 3
6 | Delivery 2 | Month 6: Week 2 | Delivery 2 | Month 6: Week 1
8 | Delivery 3/ Phase-I Closure | Month 6.5: Week 2 | Delivery 3 | Month 6.5: Week 2